## Gantt
Project Plan | [14 empty] | Legend:
[8 empty] | Project Start Date: |  |  | 2018-10-15 |  |  |  | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned |  |  |  |  | Actual
[8 empty] | Scrolling Increment: |  |  | 0
[15 empty] | October | [20 empty] | November | [27 empty] | December | [34 empty] | January | [25 empty] | February
 | time axis 2018-10-15 to 2019-02-20
ID | Component | Activity | Task | Category | Predecessor | Lag Days (Working Days) | Start | Effort (Working Days) | Task Duration | End | Responsible | Actual Start | Actual End | Progress | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
1 |  | Project Start |  |  |  |  | 2018-10-15 |  | 0 | 2018-10-15 |  |  |  | 0%
2 | Component 1 | Business Engagement | Business Engagement | Low Risk |  |  | 2018-10-15 | 1 | 1.25 | 2018-10-16 | Resource 7 | 2018-10-19 | 2018-10-23 | 100%
3 | [8 empty] | 0 |  |  |  |  | 0%
4 | [8 empty] | 0 |  |  |  |  | 0%
5 | Component 1 | Strategy Planning | Planning | Low Risk | 2 |  | 2018-10-23 | 1 | 2 | 2018-10-25 | Resource 3 |  |  | 25%
6 | Component 1 | Test Planning | Planning | Med Risk |  |  | 2018-10-25 | 1 | 1 | 2018-10-26 | Resource 8 |  |  | 0%
7 | Component 1 | Deployment Planning | Planning | High Risk | 5 |  | 2018-10-25 | 1 | 1 | 2018-10-26 | Resource 1 |  |  | 75%
8 | [8 empty] | 0 |  |  |  |  | 0%
9 | [8 empty] | 0 |  |  |  |  | 0%
10 | Component 1 | Create User Stories | Design | Low Risk | 5 |  | 2018-10-25 | 5 | 6.25 | 2018-11-02 | Resource 7 |  |  | 60%
11 | Component 1 | Create Business Process Maps | Design | On Track | 5 |  | 2018-10-25 | 5 | 6.25 | 2018-11-02 | Resource 7 |  |  | 65%
12 | Component 1 | Solution Proposal | Design | Low Risk |  |  | 2018-11-02 | 0.25 | 0.25 | 2018-11-02 | Resource 1 |  |  | 0%
13 | Component 1 | Solution Architecture | Design | Goal |  |  | 2018-11-02 | 0.25 | 0.5 | 2018-11-02 | Resource 3 |  |  | 0% | F: 2
14 | [8 empty] | 0 |  |  |  |  | 0%
15 | [8 empty] | 0 |  |  |  |  | 0%
16 | [8 empty] | 0 |  |  |  |  | 0%
17 | Component 1 | Scope Test Approach | Compatibility Testing | Med Risk | 6 |  | 2018-10-26 | 3 | 3.25 | 2018-10-31 | Resource 8 |  |  | 0%
18 | Component 1 | Complete Testing | Compatibility Testing | Low Risk |  |  | 2018-10-31 | 5 | 5.5 | 2018-11-07 | Resource 8 |  |  | 0%
19 | [8 empty] | 0 |  |  |  |  | 0%
20 | [8 empty] | 0 |  |  |  |  | 0%
21 | Component 1 | Dev System Config | Development | Low Risk | 1 |  | 2018-10-15 | 0.5 | 1 | 2018-10-16 | Resource 3 |  |  | 0%
22 | Component 1 | FAT Scope Test Approach | Development | Low Risk | 1 |  | 2018-10-15 | 0.25 | 0.75 | 2018-10-15 | Resource 5 |  |  | 0%
23 | Component 1 | FAT Script Authoring | Development | High Risk |  |  | 2018-10-15 | 2 | 5 | 2018-10-22 | Resource 5 |  |  | 0%
24 | Component 1 | FAT Complete Testing | Development | Low Risk |  |  | 2018-10-22 | 0.5 | 1.25 | 2018-10-23 | Resource 5 |  |  | 0%
25 | Component 1 | FAT Acceptance | Development | Milestone |  |  | 2018-10-23 | 0.25 | 0.75 | 2018-10-23 | Resource 5 |  |  | 0% | bar: T
26 | [8 empty] | 0 |  |  |  |  | 0%
27 | [8 empty] | 0 |  |  |  |  | 0%
28 | [8 empty] | 0 |  |  |  |  | 0%
29 | Component 1 | SIT System Config | SIT | Low Risk | 1 |  | 2018-10-15 | 1 | 2 | 2018-10-17 | Resource 3 |  |  | 0%
30 | Component 1 | Scope Test Approach | SIT | Low Risk |  |  | 2018-10-17 | 0 | 0 | 2018-10-17 | Resource 8 |  |  | 0%
31 | Component 1 | Complete Testing | SIT | Low Risk |  |  | 2018-10-17 | 0 | 0 | 2018-10-17 | Resource 8 |  |  | 0%
32 | Component 1 | Acceptance | SIT | Low Risk |  |  | 2018-10-17 | 0 | 0 | 2018-10-17 | Resource 8 |  |  | 0%
33 | [8 empty] | 0 |  |  |  |  | 0%
34 | [8 empty] | 0 |  |  |  |  | 0%
35 | [8 empty] | 0 |  |  |  |  | 0%
36 | [8 empty] | 0 |  |  |  |  | 0%
37 | Component 1 | Scope Test Approach | UAT | Low Risk | 32 |  | 2018-10-17 |  | 0 | 2018-10-17 | Resource 7 |  |  | 0%
38 | Component 1 | Complete Testing | UAT | Low Risk |  |  | 2018-10-17 |  | 0 | 2018-10-17 | Resource 7 |  |  | 0%
39 | Component 1 | Acceptance | UAT | Milestone |  |  | 2018-10-17 |  | 0 | 2018-10-17 | Resource 7 |  |  | 0% | bar: W
40 | [8 empty] | 0 |  |  |  |  | 0%
41 | [8 empty] | 0 |  |  |  |  | 0%
42 | Component 1 | Documentation | Support | Low Risk | 39 |  | 2018-10-17 | 2 | 5 | 2018-10-24 | Resource 5 |  |  | 0%
43 | Component 1 | Known Issues | Support | Low Risk |  |  | 2018-10-24 | 1 | 2.5 | 2018-10-26 | Resource 5 |  |  | 0%
44 | Component 1 | First Line Engagement | Support | Low Risk |  |  | 2018-10-26 | 0.5 | 1.25 | 2018-10-29 | Resource 5 |  |  | 0%
45 | Component 1 | Acceptance | Support | Milestone |  |  | 2018-10-29 | 0.25 | 0.75 | 2018-10-29 | Resource 5 |  |  | 0% | bar: M
46 | [8 empty] | 0 |  |  |  |  | 0%
47 | [8 empty] | 0 |  |  |  |  | 0%
48 | Component 1 | Live System Config | Implementation | Low Risk | 45 |  | 2018-10-29 | 1 | 2 | 2018-10-31 | Resource 3 |  |  | 0%
49 | Component 1 | Approach | Training | Low Risk |  |  | 2018-10-31 |  | 0 | 2018-10-31 | Resource 6 |  |  | 0%
50 | Component 1 | Materials | Training | Low Risk |  |  | 2018-10-31 |  | 0 | 2018-10-31 | Resource 6 |  |  | 0%
51 | Component 1 | Execution (SMEs) | Training | Low Risk |  |  | 2018-10-31 |  | 0 | 2018-10-31 | Resource 6 |  |  | 0%
52 | Component 1 | Execution (User Base) | Training | Low Risk |  |  | 2018-10-31 |  | 0 | 2018-10-31 | Resource 7 |  |  | 0%
53 | Component 1 | Execution | Implementation | Low Risk |  |  | 2018-10-31 |  | 0 | 2018-10-31 | Resource 9 |  |  | 0%
54 | [8 empty] | 0 |  |  |  |  | 0%
55 | [8 empty] | 0 |  |  |  |  | 0%
56 | Component 2 | Strategy Planning | Planning | Low Risk | 1 |  | 2018-10-15 | 5 | 5 | 2018-10-22 | Resource 1 |  |  | 0%
57 | Component 2 | Requirements Gathering | Design | Low Risk |  |  | 2018-10-22 | 4.25 | 6.5 | 2018-10-30 | Resource 10 |  |  | 0%
58 | Component 2 | CRM CS Create Vanilla Service / SP 2016 | Development - CRM CS | Low Risk | 56 |  | 2018-10-22 | 2 | 3 | 2018-10-25 | Resource 10 |  |  | 0%
59 | Component 2 | Hymans to Export Customisations from Prod | Development - CRM CS | Low Risk | 58 |  | 2018-10-25 | 1 | 2 | 2018-10-29 | Resource 3 |  |  | 0%
60 | Component 2 | CRM CS to Import Customisations Dev | Development - CRM CS | Low Risk |  |  | 2018-10-29 | 1 | 1.5 | 2018-10-30 | Resource 10 |  |  | 0%
61 | Component 2 | CRM CS to Install Docman | Development - CRM CS | Low Risk |  |  | 2018-10-30 | 1 | 1.5 | 2018-10-31 | Resource 10 |  |  | 0%
62 | Component 2 | Configuration Workshop | Development - CRM CS | Low Risk |  |  | 2018-10-31 | 0 | 0 | 2018-10-31 | Resource 1 |  |  | 0%
63 | Component 2 | CRM CS to complete Configuration | Development - CRM CS | Low Risk | 56 |  | 2018-10-22 | 10 | 15.5 | 2018-11-12 | Resource 10 |  |  | 0%
64 | Component 2 | CRM CS to Demo Functionality | Development - CRM CS | Low Risk |  |  | 2018-11-12 | 1 | 1.5 | 2018-11-13 | Resource 10 |  |  | 0%
65 | Component 2 | CRM CS to reconfigure based on Demo Feedback | Development - CRM CS | Low Risk |  |  | 2018-11-13 | 5 | 7.75 | 2018-11-22 | Resource 10 |  |  | 0%
66 | Component 2 | CRM CS to Demo Reconfigured solution | Development - CRM CS | Low Risk |  |  | 2018-11-22 | 1 | 1.5 | 2018-11-23 | Resource 10 |  |  | 0%
67 | Component 2 | Proceed to FAT Acceptance Gate | Development - CRM CS | Low Risk |  |  | 2018-11-23 | 1 | 1 | 2018-11-26 | Resource 1 |  |  | 0%
68 | Component 2 | FAT Scope Test Approach | Development - CRM CS | Low Risk | 1 |  | 2018-10-15 | 2 | 5 | 2018-10-22 | Resource 5 |  |  | 0%
69 | Component 2 | FAT Script Authoring | Development - CRM CS | Low Risk |  |  | 2018-10-22 | 5 | 12.5 | 2018-11-07 | Resource 5 |  |  | 0%
70 | Component 2 | FAT Complete Testing | Development - CRM CS | Low Risk | 67 |  | 2018-11-26 | 3 | 7.5 | 2018-12-05 | Resource 5 |  |  | 0%
71 | Component 2 | FAT Acceptance | Development - CRM CS | Low Risk |  |  | 2018-12-05 | 1 | 2.5 | 2018-12-07 | Resource 5 |  |  | 0%
72 | Component 2 | Post-FAT Reconfiguration | Development - CRM CS | Low Risk |  |  | 2018-12-07 | 5 | 7.75 | 2018-12-18 | Resource 10 |  |  | 0%
73 | Component 2 | FAT Complete Testing | Development - CRM CS | Low Risk |  |  | 2018-12-18 | 2 | 5 | 2019-01-04 | Resource 5 |  |  | 0%
74 | Component 2 | FAT Acceptance | Development - CRM CS | Low Risk |  |  | 2019-01-04 | 1 | 2.5 | 2019-01-08 | Resource 5 |  |  | 0%
75 | [8 empty] | 0 |  |  |  |  | 0%
76 | [8 empty] | 0 |  |  |  |  | 0%
77 | Component 2 | Import Customisations Dev | Development - Hymans | Low Risk | 74 |  | 2019-01-08 | 1 | 2 | 2019-01-10 | Resource 3 |  |  | 0%
78 | Component 2 | CRM CS to Install Docman | Development - Hymans | Low Risk |  |  | 2019-01-10 | 1 | 1.5 | 2019-01-11 | Resource 10 |  |  | 0%
79 | Component 2 | CRM CS to Import Configuration | Development - Hymans | Low Risk |  |  | 2019-01-11 | 2 | 3 | 2019-01-16 | Resource 10 |  |  | 0%
80 | Component 2 | UI/UX Configuration | Development - Hymans | Low Risk |  |  | 2019-01-16 | 5 | 10 | 2019-01-30 | Resource 3 |  |  | 0%
81 | Component 2 | UI/UX Showcase | Development - Hymans | Low Risk |  |  | 2019-01-30 | 2 | 4 | 2019-02-05 | Resource 3 |  |  | 0%
82 | Component 2 | UI/UX Reconfiguration | Development - Hymans | Low Risk |  |  | 2019-02-05 | 3 | 6 | 2019-02-13 | Resource 3 |  |  | 0%
83 | Component 2 | UI/UX Acceptance | Development - Hymans | Low Risk |  |  | 2019-02-13 | 1 | 2 | 2019-02-15 | Resource 3 |  |  | 0%
84 | Component 2 | Perform FAT | Development - Hymans | Low Risk |  |  | 2019-02-15 | 2 | 5 | 2019-02-22 | Resource 5 |  |  | 0%
85 | Component 2 | Acceptance Call | Development - Hymans | Low Risk |  |  | 2019-02-22 | 1 | 1 | 2019-02-25 | Resource 1 |  |  | 0%
86 | [8 empty] | 0 |  |  |  |  | 0%
87 | Component 2 | Live CRM into Staging | Testing (Data Migration) | Low Risk | 60 |  | 2018-10-30 | 1 | 2 | 2018-11-01 | Resource 3 |  |  | 0%
88 | Component 2 | Point Staging to SP 2016 Farm | Testing (Data Migration) | Low Risk |  |  | 2018-11-01 | 3 | 6 | 2018-11-09 | Resource 3 |  |  | 0%
89 | Component 2 | CRM CS Configure Doc Location Scripts | Testing (Data Migration) | Low Risk | 85 |  | 2019-02-25 | 2 | 3 | 2019-02-28 | Resource 10 |  |  | 0%
90 | Component 2 | CRM CS Deploy Doc Location Scripts | Testing (Data Migration) | Low Risk |  |  | 2019-02-28 | 5 | 7.75 | 2019-03-11 | Resource 10 |  |  | 0%
91 | Component 2 | Engage App Ops to perform reconcilliation / DBA? | Testing (Data Migration) | Low Risk |  |  | 2019-03-11 | 5 | 5 | 2019-03-18 | Resource 1 |  |  | 0%
92 | Component 2 | RM /LL to spot check | Testing (Data Migration) | Low Risk |  |  | 2019-03-18 | 2 | 4 | 2019-03-22 | Resource 3 |  |  | 0%
93 | Component 2 | QA to Perform Thorough Check | Testing (Data Migration) | Low Risk |  |  | 2019-03-22 | 3 | 3.25 | 2019-03-27 | Resource 8 |  |  | 0%
94 | Component 2 | Acceptance Call | Testing (Data Migration) | Low Risk |  |  | 2019-03-27 | 1 | 1 | 2019-03-28 | Resource 1 |  |  | 0%
95 | [8 empty] | 0 |  |  |  |  | 0%
96 | Component 2 | CRM CS to Install Docman | Testing (SIT / VPT) | Low Risk | 1 |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 10 |  |  | 0%
97 | Component 2 | CRM CS to Import Configuration | Testing (SIT / VPT) | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 10 |  |  | 0%
98 | Component 2 | LL/RM to Perform FAT | Testing (SIT / VPT) | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
99 | Component 2 | QA/RM/LL to configure test scripts | Testing (SIT / VPT) | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 8 |  |  | 0%
100 | Component 2 | QA to Perform SIT / VPT | Testing (SIT / VPT) | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 8 |  |  | 0%
101 | Component 2 | Acceptance Call | Testing (SIT / VPT) | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 1 |  |  | 0%
102 | [8 empty] | 0 |  |  |  |  | 0%
103 | Component 2 | Define UAT Approach | Implementation | Low Risk | 1 |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 1 |  |  | 0%
104 | Component 2 | Compile UAT Scripts (With LS) | Testing (UAT) | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 6 |  |  | 0%
105 | Component 2 | Perform UAT | Testing (UAT) | Low Risk | 94 |  | 2019-03-28 | 10 | 10 | 2019-04-11 | Resource 11 |  |  | 0%
106 | Component 2 | UAT Acceptance Call | Testing (UAT) | Low Risk |  |  | 2019-04-11 | 1 | 1 | 2019-04-12 | Resource 1 |  |  | 0%
107 | Component 2 | Support Acceptance Call | Testing (UAT) | Low Risk | 105 |  | 2019-04-11 | 1 | 1 | 2019-04-12 | Resource 1 |  |  | 0%
108 | [8 empty] | 0 |  |  |  |  | 0%
109 | [8 empty] | 0 |  |  |  |  | 0%
110 | Component 2 | Documentation | Support | Low Risk | 1 |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
111 | Component 2 | Known Issues | Support | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
112 | Component 2 | First Line Engagement | Support | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
113 | Component 2 | Acceptance | Support | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
114 | [8 empty] | 0 |  |  |  |  | 0%
115 | [8 empty] | 0 |  |  |  |  | 0%
116 | Component 2 | Define Deployment Strategy | Implementation | Low Risk |  |  |  |  | 0 |  | Resource 1 |  |  | 0%
117 | Component 2 | Install Docman - Prod | Implementation | Low Risk | 107 |  | 2019-04-12 | 2 | 3 | 2019-04-17 | Resource 10 |  |  | 0%
118 | Component 2 | Import CRM Config | Implementation | Low Risk |  |  | 2019-04-17 | 3 | 6 | 2019-04-25 | Resource 3 |  |  | 0%
119 | Component 2 | Execute Document Location Scripts | Implementation | Low Risk |  |  | 2019-04-25 | 2 | 4 | 2019-05-01 | Resource 3 |  |  | 0%
120 | Component 2 | Smoke Test | Implementation | Low Risk |  |  | 2019-05-01 | 2 | 5 | 2019-05-08 | Resource 5 |  |  | 0%
121 | [8 empty] | 0 |  |  |  |  | 0%
122 | Component 3 | User Stories | Business Engagement | Low Risk | 1 | 12 | 2018-10-31 | 1 | 1.25 | 2018-11-01 | Resource 7 | 2018-10-31 | 2018-11-06 | 0%
123 | Component 3 | Business Processes | Business Engagement | Low Risk |  |  | 2018-11-06 | 0 | 0 | 2018-11-06 | Resource 7 | 2018-10-31 | 2018-11-06 | 0%
124 | Component 3 | Functional Requirements | Design | Low Risk |  |  | 2018-11-06 | 2 | 4 | 2018-11-12 | Resource 3 |  |  | 0%
125 | Component 3 | Solution Proposal | Design | Low Risk |  |  | 2018-11-12 | 1 | 2 | 2018-11-14 | Resource 3 |  |  | 0%
126 | Component 3 | Solution Acceptance | Design | Low Risk |  |  | 2018-11-14 | 1 | 1 | 2018-11-15 | Resource 1 |  |  | 0%
127 | Component 3 | Prototype | Development | Low Risk |  |  | 2018-11-15 | 5 | 10 | 2018-11-29 | Resource 3 |  |  | 0%
128 | Component 3 | Prototype Review | Development | Low Risk |  |  | 2018-11-29 | 2 | 2 | 2018-12-03 | Resource 1 |  |  | 0%
129 | Component 3 | Release Candidate | Development | Low Risk |  |  | 2018-12-03 | 5 | 10 | 2018-12-17 | Resource 3 |  |  | 0%
130 | Component 3 | Release Candidate Review | Development | Low Risk |  |  | 2018-12-17 | 2 | 2 | 2018-12-19 | Resource 1 |  |  | 0%
131 | Component 3 | FAT Scope Test Approach | Development | Low Risk | 122 |  | 2018-11-06 | 2 | 5 | 2018-11-13 | Resource 5 |  |  | 0%
132 | Component 3 | FAT Script Authoring | Development | Low Risk |  |  | 2018-11-13 | 3 | 7.5 | 2018-11-22 | Resource 5 |  |  | 0%
133 | Component 3 | FAT Testing | Development | Low Risk | 130 |  | 2018-12-19 | 3 | 7.5 | 2019-01-09 | Resource 5 |  |  | 0%
134 | Component 3 | Post-FAT Reconfiguration | Development | Low Risk |  |  | 2019-01-09 | 2 | 4 | 2019-01-15 | Resource 3 |  |  | 0%
135 | Component 3 | FAT Testing Complete | Development | Low Risk |  |  | 2019-01-15 | 2 | 5 | 2019-01-22 | Resource 5 |  |  | 0%
136 | Component 3 | FAT Acceptance | Development | Low Risk |  |  | 2019-01-22 | 1 | 2.5 | 2019-01-24 | Resource 5 |  |  | 0%
137 | [8 empty] | 0 |  |  |  |  | 0%
138 | Component 3 | Deployment to Staging | Testing (SIT / VPT) | Low Risk | 136 |  | 2019-01-24 | 1 | 2 | 2019-01-28 | Resource 3 |  |  | 0%
139 | Component 3 | Staging FAT | Testing (SIT / VPT) | Low Risk |  |  | 2019-01-28 | 2 | 5 | 2019-02-04 | Resource 5 |  |  | 0%
140 | Component 3 | Testing Scope | Testing (SIT / VPT) | Low Risk | 122 |  | 2018-11-06 |  | 0 | 2018-11-06 | Resource 8 |  |  | 0%
141 | Component 3 | Test Scripts | Testing (SIT / VPT) | Low Risk |  |  | 2018-11-06 |  | 0 | 2018-11-06 | Resource 8 |  |  | 0%
142 | Component 3 | Test Execution | Testing (SIT / VPT) | Low Risk | 139 |  | 2019-02-04 | 3 | 3.25 | 2019-02-07 | Resource 8 |  |  | 0%
143 | Component 3 | Post-Testing Reconfiguration | Testing (SIT / VPT) | Low Risk |  |  | 2019-02-07 | 3 | 6 | 2019-02-15 | Resource 3 |  |  | 0%
144 | Component 3 | Test Execution | Testing (SIT / VPT) | Low Risk |  |  | 2019-02-15 | 3 | 3.25 | 2019-02-20 | Resource 8 |  |  | 0%
145 | Component 3 | Test Acceptance | Testing (SIT / VPT) | Low Risk |  |  | 2019-02-20 | 1 | 1 | 2019-02-21 | Resource 1 |  |  | 0%
146 | [8 empty] | 0 |  |  |  |  | 0%
147 | Component 3 | Testing Scope | Testing (UAT) | Low Risk | 122 |  | 2018-11-06 |  | 0 | 2018-11-06 | Resource 7 |  |  | 0%
148 | Component 3 | Test Scripts | Testing (UAT) | Low Risk |  |  | 2018-11-06 |  | 0 | 2018-11-06 | Resource 7 |  |  | 0%
149 | Component 3 | Test Execution | Testing (UAT) | Low Risk | 145 |  | 2019-02-21 | 5 | 6.25 | 2019-03-01 | Resource 7 |  |  | 0%
150 | Component 3 | Post-Testing Reconfiguration | Testing (UAT) | Low Risk |  |  | 2019-03-01 | 3 | 6 | 2019-03-11 | Resource 3 |  |  | 0%
151 | Component 3 | Test Execution | Testing (UAT) | Low Risk |  |  | 2019-03-11 | 3 | 3.75 | 2019-03-14 | Resource 7 |  |  | 0%
152 | Component 3 | Acceptance | Testing (UAT) | Low Risk |  |  | 2019-03-14 | 1 | 1 | 2019-03-15 | Resource 1 |  |  | 0%
153 | [8 empty] | 0 |  |  |  |  | 0%
154 | Component 3 | Documentation | Support | Low Risk | 1 |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
155 | Component 3 | Known Issues | Support | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
156 | Component 3 | First Line Engagement | Support | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
157 | Component 3 | Acceptance | Support | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 5 |  |  | 0%
158 | [8 empty] | 0 |  |  |  |  | 0%
159 | Component 3 | Approach | Implementation | Low Risk | 122 |  | 2018-11-06 |  | 0 | 2018-11-06 | Resource 7 |  |  | 0%
160 | Component 3 | Deployment to Live | Implementation | Low Risk | 152 |  | 2019-03-15 | 1 | 2 | 2019-03-19 | Resource 3 |  |  | 0%
161 | Component 3 | Smoke Test | Implementation | Low Risk |  |  | 2019-03-19 | 2 | 5 | 2019-03-26 | Resource 5 |  |  | 0%
162 | [8 empty] | 0 |  |  |  |  | 0%
163 | Component 3 | Review User Stories | Training | Low Risk | 122 |  | 2018-11-06 | 2 | 2.75 | 2018-11-08 | Resource 6 |  |  | 0%
164 | Component 3 | Review Business Process Maps | Training | Low Risk | 122 |  | 2018-11-06 | 2 | 2.75 | 2018-11-08 | Resource 6 |  |  | 0%
165 | Component 3 | Training Approach | Training | Low Risk |  |  | 2018-11-08 | 2 | 2.75 | 2018-11-12 | Resource 6 |  |  | 0%
166 | Component 3 | Materials | Training | Low Risk |  |  | 2018-11-12 | 5 | 7.25 | 2018-11-21 | Resource 6 |  |  | 0%
167 | Component 3 | Feedback Forms | Training | Low Risk |  |  | 2018-11-21 |  | 0 | 2018-11-21 | Resource 6 |  |  | 0%
168 | Component 3 | Training Delivery | Training | Low Risk | 161 |  | 2019-03-26 | 10 | 14.25 | 2019-04-15 | Resource 6 |  |  | 0%
169 | Component 3 | Mop-ups | Training | Low Risk |  |  | 2019-04-15 | 5 | 7.25 | 2019-04-24 | Resource 6 |  |  | 0%
170 | [8 empty] | 0 |  |  |  |  | 0%
171 | Component 3 | Go-Live | Implementation | Low Risk | 169 |  | 2019-04-24 | 1 | 2 | 2019-04-26 | Resource 3 |  |  | 0%
172 | [8 empty] | 0 |  |  |  |  | 0%
173 | [8 empty] | 0 |  |  |  |  | 0%
174 | Component 4 | Task 1 | Configuration | Low Risk | 1 |  | 2018-10-15 |  | 0 | 2018-10-15 |  |  |  | 0%
175 | Component 4 | Task 2 | Data Migration | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 |  |  |  | 0%
176 | Component 4 | Task 3 |  | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
177 | [8 empty] | 0
178 | [8 empty] | 0
179 | [8 empty] | 0
180 | Component 5 | Determine User Base | Business Engagement | Low Risk | 1 |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 7
181 | Component 5 | Determine SMEs | Business Engagement | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 7
182 | Component 5 | Review User Stories | Planning | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 6
183 | Component 5 | Review Business Process Maps | Planning | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 6
184 | Component 5 | Determine Resourcews (SMEs) | Planning | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15 | Resource 7
185 | Component 5 | Training Approach | Design | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
186 | Component 5 | Materials | Development | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
187 | Component 5 | Feedback Forms | Development | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
188 | Component 5 | New System Showcase | Delivery | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
189 | Component 5 | SME Training | Delivery | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
190 | Component 5 | SME Governance | Delivery | Low Risk |  |  | 2018-10-15 |  | 0 | 2018-10-15
191 | [8 empty] | 0
192 | [8 empty] | 0
193 | [8 empty] | 0
194 | [8 empty] | 0
195 | Component 6 | Evaluation | Evaluation | Low Risk | 120 |  | 2019-05-08 |  | 0 | 2019-05-08
196 | [8 empty] | 0
197 | [8 empty] | 0
198 | [8 empty] | 0
199 | [8 empty] | 0
200 | [8 empty] | 0
201 | [8 empty] | 0
202 | [8 empty] | 0
203 | [8 empty] | 0
204 | [8 empty] | 0
205 | [8 empty] | 0
206 | [8 empty] | 0
207 | [8 empty] | 0
208 | [8 empty] | 0
209 | [8 empty] | 0
210 | [8 empty] | 0
211 | [8 empty] | 0
212 | [8 empty] | 0
213 | [8 empty] | 0
214 | [8 empty] | 0
215 | [8 empty] | 0
216 | [8 empty] | 0
217 | [8 empty] | 0
218 | [8 empty] | 0
219 | [8 empty] | 0
220 | [8 empty] | 0
221 | [8 empty] | 0
222 | [8 empty] | 0
223 | [8 empty] | 0
224 | [8 empty] | 0
225 | [8 empty] | 0
226 | [8 empty] | 0
227 | [8 empty] | 0
228 | [8 empty] | 0
229 | [8 empty] | 0
230 | [8 empty] | 0
231 | [8 empty] | 0
232 | [8 empty] | 0
233 | [8 empty] | 0
234 | [8 empty] | 0
235 | [8 empty] | 0
236 | [8 empty] | 0
237 | [8 empty] | 0
238 | [8 empty] | 0
239 | [8 empty] | 0
240 | [8 empty] | 0
241 | [8 empty] | 0
242 | [8 empty] | 0
243 | [8 empty] | 0

## Project Personnel
Name | Profile
Resource 1 | 100%
Resource 2 | 60%
Resource 3 | 50%
Resource 4 | 60%
Resource 5 | 40%
Resource 6 | 70%
Resource 7 | 80%
Resource 8 | 90%
Resource 9 | 100%
Resource 10 | 65%
Resource 11 | 100%

## Project Summary
High-Level Summary Dates |  |  | Mid-Level Summary Dates
Component | Start Date | End Date | Component | Task | Start Date | End Date
Component 1 | 2018-10-15 | 2018-11-07 | Component 1 | Business Engagement | 2018-10-15 | 2018-10-16
Component 2 | 2018-10-15 | 2019-05-08 | Component 1 | Planning | 2018-10-23 | 2018-10-26
Component 3 | 2018-10-15 | 2019-04-26 | Component 1 | Design | 2018-10-25 | 2018-11-02
Component 4 | 2018-10-15 | 2018-10-15 | Component 1 | Compatibility Testing | 2018-10-26 | 2018-11-07
Component 5 | 2018-10-15 | 2018-10-15 | Component 1 | Development | 2018-10-15 | 2018-10-23
Component 6 | 2019-05-08 | 2019-05-08 | Component 1 | SIT | 2018-10-15 | 2018-10-17
|  |  | Component 1 | UAT | 2018-10-17 | 2018-10-17
|  |  | Component 1 | Support | 2018-10-17 | 2018-10-29
|  |  | Component 1 | Implementation | 2018-10-29 | 2018-10-31
|  |  | Component 1 | Training | 2018-10-31 | 2018-10-31
|  |  | Component 2 | Planning | 2018-10-15 | 2018-10-22
|  |  | Component 2 | Design | 2018-10-22 | 2018-10-30
|  |  | Component 2 | Development - CRM CS | 2018-10-15 | 2019-01-08
|  |  | Component 2 | Development - Hymans | 2019-01-08 | 2019-02-25
|  |  | Component 2 | Testing (Data Migration) | 2018-10-30 | 2019-03-28
|  |  | Component 2 | Testing (SIT / VPT) | 2018-10-15 | 2018-10-15
|  |  | Component 2 | Implementation | 2018-10-15 | 2019-05-08
|  |  | Component 2 | Testing (UAT) | 2018-10-15 | 2019-04-12
|  |  | Component 2 | Support | 2018-10-15 | 2018-10-15
|  |  | Component 3 | Business Engagement | 2018-10-31 | 2018-11-06
|  |  | Component 3 | Design | 2018-11-06 | 2018-11-15
|  |  | Component 3 | Development | 2018-11-06 | 2019-01-24
|  |  | Component 3 | Testing (SIT / VPT) | 2018-11-06 | 2019-02-21
|  |  | Component 3 | Testing (UAT) | 2018-11-06 | 2019-03-15
|  |  | Component 3 | Support | 2018-10-15 | 2018-10-15
|  |  | Component 3 | Implementation | 2018-11-06 | 2019-04-26
|  |  | Component 4 | Configuration | 2018-10-15 | 2018-10-15
|  |  | Component 4 | Data Migration | 2018-10-15 | 2018-10-15
|  |  | Component 5 | Business Engagement | 2018-10-15 | 2018-10-15
|  |  | Component 5 | Planning | 2018-10-15 | 2018-10-15
|  |  | Component 5 | Design | 2018-10-15 | 2018-10-15
|  |  | Component 5 | Development | 2018-10-15 | 2018-10-15
|  |  | Component 5 | Delivery | 2018-10-15 | 2018-10-15
|  |  | Component 6 | Evaluation | 2019-05-08 | 2019-05-08
Formulas:
Start Date = MINIFS(MidLevelSummary[Start Date],MidLevelSummary[Component],HighLevelSummary[[#This Row],[Component]])
Start Date = MINIFS(Milestones[Start],Milestones[Component],MidLevelSummary[[#This Row],[Component]],Milestones[Task],MidLevelSummary[[#This Row],[Task]])
End Date = MAXIFS(MidLevelSummary[End Date],MidLevelSummary[Component],HighLevelSummary[[#This Row],[Component]])
End Date = MAXIFS(Milestones[End],Milestones[Component],MidLevelSummary[[#This Row],[Component]],Milestones[Task],MidLevelSummary[[#This Row],[Task]])

## calcs
Holidays
2018-12-24
2018-12-25
2018-12-26
2018-12-27
2018-12-28
2018-12-29
2018-12-30
2018-12-31
2019-01-01
2019-01-02